GCX | GLOBAL CUSTOMER EXPERIENCE

GCX Change Enablement Toolkit Project Delivery ¦ Leadership Enablement

|  | WHY THIS EXISTS Purpose A guided operating system for landing change - helping GCX choose the right support level, prepare impacted teams, activate leaders and managers, manage saturation, and measure whether adoption actually happened. |
| --- | --- |

|  | AUDIENCE Designed for GCX leaders, people managers, project teams, change leads, Gold/Silver/Bronze users, and self-service audiences. |
| --- | --- |

|  | SELF-SERVICE DESIGN Design intent This toolkit is built for fast navigation: guided paths, template cards, tier-based journeys, and templates that are practical in real work. |
| --- | --- |

| eBay color | Meaning | Use |
| --- | --- | --- |
| Blue | Guidance / structure / decision support | Decision tools, operating guidance, project delivery navigation |
| Red | Risk / saturation / action required | Risk logs, saturation flags, escalation prompts |
| Yellow | Readiness / watch area / prioritization | Go-live readiness, watch items, prioritization discussions |
| Green | Adoption / progress / go-live confidence | Adoption measures, leadership rhythms, reinforcement |

# Start Here: Choose Your Path

Start with what you are trying to do, then jump to the right tool or journey.

| I need to... | Go to | Primary output |
| --- | --- | --- |
| Start a project or define a change | Project Delivery - Change Snapshot Template | Plain-language definition of what changes and what people must do differently |
| Assess change impact | Project Delivery - Change Impact Canvas | Clear view of who is impacted, what changes for them, adoption risk, and support needed |
| Decide Gold / Silver / Bronze | Project Delivery - Support Level Selector | Right-sized support level and minimum required assets |
| Check if the audience can absorb the change | Project Delivery - Audience Load Check | Saturation risk and leader decision |
| Prepare for launch | Project Delivery - Launch Confidence Check | Go / go with mitigations / no-go decision |
| Measure whether adoption happened | Project Delivery - Adoption Intelligence Scorecard | Behavior and business outcome signals |
| Equip managers to reinforce change | Leadership Enablement - Manager Action Card | Say / do / watch / escalate / recognize guidance |
| Run an always-on leadership rhythm | Leadership Enablement - Weekly Leader Guidance and Signals Pack | Consistent leader and manager action loop |
| Connect change to Our DNA | Leadership Enablement - DNA Thread Builder | Culture, customer impact, belonging, and responsible AI in normal rhythms |

| Project Delivery From project idea to adoption measurement. | Leadership Enablement From leader message to manager-led adoption. |
| --- | --- |
| Gold / Silver / Bronze Right-size support and minimum required tools. |  |

# Template Journeys: Navigate by Intent

These journeys show which templates to use based on the work in front of you.

| Journey | Use these templates | Best for |
| --- | --- | --- |
| Launching a high-impact change | Change Snapshot -> Change Impact Canvas -> Support Level Selector -> Audience Impact Mapper -> Behavior Shift Canvas -> One-Page Change Sprint Plan -> Leader Cascade Brief -> Manager Action Card -> Audience Load Check -> Launch Confidence Check -> Adoption Intelligence Scorecard | Gold / complex Silver initiatives |
| Running a Bronze self-service change | Change Snapshot -> 60-Second Message Builder -> FAQ Builder -> Manager Script -> Launch Checklist -> Basic Success Measure | Low complexity, clear-owner changes |
| Equipping managers | Manager Action Card -> Manager What To Do Next -> Signals Pack -> Top Heard / Top Changed -> Adoption Scorecard | Manager-led adoption |
| Connecting change to Our DNA | DNA Thread Builder -> Monthly DNA Leader Message -> Manager Cascade 3/2/1 -> Recognition Prompts -> AI Responsibility Prompt | Leadership rhythm and culture activation |
| Responding to saturation risk | Audience Load Check -> Monthly Adoption and Org Health Checkpoint -> Leader Decision Log -> Updated Manager Guidance | Leaders, portfolio owners, change leads |

# Gold / Silver / Bronze: Minimum Viable Change Plan

The service model is designed to protect capacity while giving each initiative the minimum viable level of change support required for adoption.

| Tier | Use when | Minimum required assets | Operating mindset |
| --- | --- | --- | --- |
| Gold | High-impact, enterprise-wide, high-risk, saturated, or manager-dependent change. | Change Snapshot; Change Impact Canvas; Support Level Selector; Audience Impact Mapper; Behavior Shift Canvas; Change Sprint Plan; Leader Cascade; Manager Action Card; Audience Load Check; Launch Confidence Check; Adoption Intelligence Scorecard. | This requires orchestration, not just communication. |
| Silver | Medium-impact change with manageable behavior shift, some manager dependency, and visible but limited operational risk. | Change Snapshot; Change Impact Canvas; Support Level Selector; Audience Impact Mapper; Lean Plan; Manager Action Card; Readiness Check; Basic Adoption Measures. | This needs structure, but not full orchestration. |
| Bronze | Low-complexity, limited audience impact, low risk, minimal behavior change, clear owner and launch path. | Change Snapshot; 60-Second Message Builder; FAQ Builder; Manager Script; Launch Checklist; Basic Success Measure. | The toolkit is the support model. The project should move without dedicated change lead support. |

SECTION

# Section 1 | Project Delivery

From project idea to adoption measurement. This section gives project teams and change leads one practical way to define the change, right-size support, plan enablement, prepare for launch, manage saturation, track risk, and measure adoption.

|  | PRINCIPLE Project delivery principle Projects do not land because a plan says they launched. They land when impacted teams understand what changed, know what to do differently, and receive reinforcement in their normal ways of working. |
| --- | --- |

| Stage | Question | Output | Primary template |
| --- | --- | --- | --- |
| 1. Define | What is changing? | Plain-language definition | Change Snapshot Template |
| 2. Assess | Who is impacted? | Impact + support needs | Change Impact Canvas |
| 3. Size | Support needed? | Gold / Silver / Bronze | Support Level Selector |
| 4. Map | Who needs what? | Audience approach | Audience Impact Mapper |
| 5. Design | Behavior shift? | Before / after behavior | Behavior Shift Canvas |
| 6. Plan | How will it land? | Sprint plan | One-Page Change Sprint Plan |
| 7. Sequence | Can they absorb it? | Saturation decision | Audience Load Check |
| 8. Gate | Ready to launch? | Go / no-go | Launch Confidence Check |
| 9. Reinforce | Are managers ready? | Manager actions | Manager Action Card |
| 10. Measure | Is behavior changing? | Adoption signals | Adoption Intelligence Scorecard |

## Project Delivery Templates

| Change Snapshot Template Define the change in human terms before planning begins. | Change Impact Canvas Understand who is impacted, what changes for them, and what support is needed. |
| --- | --- |
| Support Level Selector Right-size Gold / Silver / Bronze support based on adoption risk. | Audience Impact Mapper Segment audiences by impact, influence, and enablement need. |
| Behavior Shift Canvas Clarify the before-and-after behavior required for adoption. | One-Page Change Sprint Plan Create a sharp, execution-ready plan for how the change will land. |
| 60-Second Message and FAQ Builder Draft simple, consistent communications and FAQs fast. | Audience Load Check Identify saturation and sequencing risk before launch dates are locked. |
| Launch Confidence Check Make a go-live decision, not just a date. | Adoption Friction Tracker Track resistance early and convert signals into action. |
| Adoption Intelligence Scorecard Measure behavior change and business outcomes, not just activity. | Bronze Self-Service Pack Run low-complexity changes using self-service guidance without dedicated CM support. |
| AI Change Copilot Prompts Accelerate drafting, synthesis, and tailoring with human review. |  |

TEMPLATE 01 | DECISION TEMPLATE

# Change Snapshot Template

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Bronze users | At intake or before planning begins | 15 minutes | Clear definition of what changes, who is impacted, and what behavior must shift | Decision Template |

Turns project language into plain-language change impact and makes the human behavior shift visible at intake.

| Field | Prompt / Fill-in |
| --- | --- |
| Initiative name | [Insert name] |
| Workstream / portfolio | [Insert workstream] |
| Business owner / sponsor | [Insert owner] |
| What is changing? | [Describe in one or two sentences] |
| Why now? | [Business, customer, teammate, or operational reason] |
| Who is impacted? | [Teams, roles, regions, partner groups] |
| What is not changing? | [Clarify what remains stable to reduce noise] |
| What will people do differently? | [Observable behavior shift] |
| What decision is needed? | [Timing / scope / support / sequencing / resource] |
| Risk if adoption is low | [Customer, operational, teammate, performance, or compliance impact] |

|  | USEFULNESS CHECK How to make this useful Strong test: a busy manager can read this and explain what their team needs to do differently in less than one minute. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 02 | DECISION TEMPLATE

# Change Impact Canvas

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Leaders, Business Owners | At intake and before launch dates are locked | 20 minutes | Clear view of impact, risk, support, and leader decision | Decision Template |

Shows who is impacted, what changes for them, and what support is needed to make adoption stick.

| Field | Prompt / Fill-in |
| --- | --- |
| Impacted audience | Which teams, roles, regions, partner groups, or leaders are impacted? |
| What changes for them? | Process / role / tool / workflow / decision / expectation. |
| What is not changing? | What remains stable to reduce noise and uncertainty? |
| Behavior shift | Today: [current behavior] / Future: [new behavior]. |
| Adoption difficulty | Low / Medium / High - why? |
| Manager role | What must managers say, do, watch for, escalate, or recognize? |
| Support needed | Comms / manager guide / job aid / training / office hours / FAQ. |
| Saturation risk | Green / Amber / Red - what else is landing for this audience? |
| Decision needed | Timing / scope / support / sequencing / resourcing. Confirm the 30 / 60 / 90 day proof of adoption. |

|  | USEFULNESS CHECK How to make this useful Keep it practical: who is impacted, what behavior must change, what support is needed, and what decision leaders need to make. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 03 | DECISION TEMPLATE

# Support Level Selector

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Change Leads, Leaders, Project Teams | During intake and before delivery planning is locked | 10 minutes | Tier decision and minimum required toolset | Decision Template |

Creates a more objective Gold / Silver / Bronze recommendation based on impact, complexity, timing, and adoption risk.

| Field | Prompt / Fill-in |
| --- | --- |
| Audience impact | Low = 1 / Medium = 2 / High = 3 |
| Behavior shift | Awareness only = 1 / workflow change = 2 / role or process shift = 3 |
| Operational risk | Low = 1 / Moderate = 2 / High customer or service risk = 3 |
| Manager dependency | Minimal = 1 / Some reinforcement = 2 / Managers critical = 3 |
| Saturation timing | Low-change period = 1 / moderate overlap = 2 / peak window = 3 |
| Total score | 5-7 Bronze / 8-11 Silver / 12-15 Gold |
| Recommended tier | [Gold / Silver / Bronze] |
| Minimum required support | [List assets and interventions] |
| Decision owner | [Change Lead / Hub / Sponsor] |

|  | USEFULNESS CHECK How to make this useful Do not let urgency or stakeholder volume override the score. If the audience is saturated or managers are critical, move the tier up. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 04 | DECISION TEMPLATE

# Audience Impact Mapper

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads | Before communications, training, or manager assets are drafted | 20 minutes | Audience-specific engagement approach | Decision Template |

Segments audiences by impact, influence, and enablement need so teams avoid one-size-fits-all messaging.

| Field | Prompt / Fill-in |
| --- | --- |
| Audience | [Leaders / managers / frontline teams / project team / partner group] |
| Impact level | High / Medium / Low |
| Influence level | High / Medium / Low |
| What they need | [Decision clarity / context / role actions / training / job aid] |
| Engagement approach | [Leader session / manager pack / comms / huddle / AMA / training] |
| Owner | [Person accountable] |
| Message depth | [Need-to-know / context / detailed enablement] |
| Feedback route | [Where questions or friction will be captured] |

|  | USEFULNESS CHECK How to make this useful Leaders need decisions and trade-offs. Managers need actions and FAQs. Frontline teams need what changes, what to do, and where to get help. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 05 | ADOPTION TEMPLATE

# Behavior Shift Canvas

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, People Managers | When the change requires people to work differently | 20 minutes | Before / after behavior, friction, and adoption proof | Adoption Template |

Keeps the focus on adoption by defining the before-and-after behaviors required for the change to stick.

| Field | Prompt / Fill-in |
| --- | --- |
| Audience / role | [Insert role or team] |
| Today | [Current behavior, workaround, habit, or decision path] |
| Future | [Expected behavior after launch] |
| Expected friction | [What will feel difficult, unclear, or annoying?] |
| Manager reinforcement needed | [What managers must say, do, watch, or coach] |
| Support needed | [Comms / job aid / training / office hours / in-flow support] |
| 30-day adoption signal | [What shows the new behavior is happening?] |
| 60/90-day sustain signal | [What shows behavior is sticking?] |

|  | USEFULNESS CHECK How to make this useful If the future behavior cannot be described clearly, the change is not ready to launch. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 06 | GUIDANCE TEMPLATE

# One-Page Change Sprint Plan

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads | After change definition, tiering, and audience mapping | 30 minutes | One-page plan with owners, timing, risks, and readiness status | Guidance Template |

Replaces heavy change plans with a concise, execution-ready view of how the change will land.

| Field | Prompt / Fill-in |
| --- | --- |
| Change objective | [What this change needs to achieve] |
| Target audience | [Who is impacted] |
| Behavior shift | Before: [current] / After: [future] |
| Support tier | Gold / Silver / Bronze |
| Core interventions | [Leader cascade / manager card / training / job aid / go-live comms / adoption tracking] |
| Owners | [Who owns each intervention] |
| Timing | [Dates and milestones] |
| Top risks | [Risk 1 / risk 2 / risk 3] |
| Go-live readiness | Green / Amber / Red |

|  | USEFULNESS CHECK How to make this useful Every intervention must have an owner, a date, and an adoption purpose. Delete anything that does not help the behavior shift happen. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 07 | GUIDANCE TEMPLATE

# 60-Second Message and FAQ Builder

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Bronze users, Change Leads | When a project needs a simple self-service message or FAQ | 15 minutes | A scannable message and top FAQs | Guidance Template |

Builds clear, consistent, practical change communications without over-engineering.

| Field | Prompt / Fill-in |
| --- | --- |
| Why this matters | [Business, customer, teammate, or operational value] |
| What is changing | [Plain-language change] |
| What you need to do | [Specific action] |
| When this starts | [Date / phase] |
| Where to get help | [Link, channel, owner] |
| FAQ: What is changing? | [Answer] |
| FAQ: Who is impacted? | [Answer] |
| FAQ: What is not changing? | [Answer] |
| FAQ: What action is required? | [Answer] |
| FAQ: Where do I get help? | [Answer] |

|  | USEFULNESS CHECK How to make this useful One clear ask. Correct dates. Acronyms defined. Links tested. Message scannable in under 60 seconds. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 08 | RISK TEMPLATE

# Audience Load Check

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Leaders | Before launch timing is committed | 15 minutes | Saturation risk and leader decision | Risk Template |

Identifies overlap, capacity risk, and sequencing decisions before launch dates are locked.

| Field | Prompt / Fill-in |
| --- | --- |
| Proposed launch date | [Date] |
| Audience impacted | [Teams / regions / roles] |
| Other changes landing | [List overlapping initiatives] |
| Audience overlap | High / Medium / Low |
| Peak operating period? | Yes / No / Unknown |
| Saturation risk | Green / Amber / Red |
| Mitigation options | Proceed / sequence / reduce scope / move timing / combine / add support |
| Leader decision required | [Specific decision needed] |

|  | USEFULNESS CHECK How to make this useful Saturation is a leadership decision, not a comms problem. Ask: are we asking the same audience to absorb too much at once? |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 09 | READINESS TEMPLATE

# Launch Confidence Check

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Leaders | Two to four weeks before go-live and again at launch readiness review | 20 minutes | Go / go with mitigations / no-go decision | Readiness Template |

Makes go-live a decision rather than a date on a plan.

| Field | Prompt / Fill-in |
| --- | --- |
| Leader alignment | Green / Amber / Red - notes |
| Manager readiness | Green / Amber / Red - notes |
| Audience understanding | Green / Amber / Red - notes |
| Training / job aids | Green / Amber / Red - notes |
| Support model | Green / Amber / Red - notes |
| Calendar / saturation | Green / Amber / Red - notes |
| Adoption metrics | Green / Amber / Red - notes |
| Decision | Go / Go with mitigations / No-go |
| Required actions before launch | [Action / owner / date] |

|  | USEFULNESS CHECK How to make this useful A red item does not automatically mean no-go. It does mean the mitigation and owner must be explicit before launch. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 10 | RISK TEMPLATE

# Adoption Friction Tracker

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Managers | During readiness, launch, and post-launch reinforcement | 15 minutes weekly | Prioritized resistance signals, owners, and actions | Risk Template |

Tracks resistance early and converts signals into specific action.

| Field | Prompt / Fill-in |
| --- | --- |
| Signal | [Low usage / workarounds / repeated questions / escalations / manager non-reinforcement] |
| Source | [Managers / frontline teams / data / support channel / telemetry] |
| Severity | Low / Medium / High |
| Likely cause | [Timing conflict / unclear workflow / unclear rationale / low confidence] |
| Action | [What will be done] |
| Owner | [Name] |
| Due date | [Date] |
| Resolved? | Yes / No / monitoring |

|  | USEFULNESS CHECK How to make this useful Look for hidden resistance in behavior, not just survey sentiment. Neutral sentiment with continued workarounds is still resistance. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 11 | ADOPTION TEMPLATE

# Adoption Intelligence Scorecard

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Leaders | At readiness review, launch, and 30/60/90-day checkpoints | 30 minutes | Decision-ready adoption and outcome view | Adoption Template |

Separates what was delivered from what changed, then links adoption to operational outcomes.

| Field | Prompt / Fill-in |
| --- | --- |
| Activity | Did we execute? Comms, sessions, packs, job aids, office hours |
| Reach | Did people receive it? Opens, attendance, manager briefings, huddle reach |
| Behavior | Are people working differently? Usage, compliance, workflow completion, observed behavior |
| Outcome | Did performance improve? AHT, FCR, CSAT, quality, productivity, escalation reduction |
| Decision triggered | Continue / reinforce / redesign / sequence / escalate / sustain |
| 30-day view | [Early usage and friction] |
| 60-day view | [Sustained behavior and manager confidence] |
| 90-day view | [Business outcome and handoff to BAU] |

|  | USEFULNESS CHECK How to make this useful The scorecard should answer: what is landing, what is not, where to intervene, and which business outcomes are moving. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 12 | GUIDANCE TEMPLATE

# Bronze Self-Service Pack

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Bronze users, Project Teams | For low-risk, low-complexity changes with a clear owner and launch path | 30 minutes | Change summary, message, FAQ, manager script, checklist, success measure | Guidance Template |

Enables lower-complexity changes to move quickly using self-service guidance without adding unnecessary load to the Change team.

| Field | Prompt / Fill-in |
| --- | --- |
| Quick change summary | What is changing / who is impacted / when it goes live / what people need to do |
| Message builder | Why this matters / what is changing / what you need to do / where to get help |
| Manager script | Team, this change means [impact]. The action I need from you is [behavior]. Use [support route] for questions. |
| FAQ builder | What is changing / who is impacted / when does this start / what action is required / where do I get help |
| Launch checklist | Summary complete / audience identified / message drafted / manager script ready / FAQ published / success measure defined |
| Basic success measure | [One measure that proves the change landed] |

|  | USEFULNESS CHECK How to make this useful Bronze does not mean unsupported. It means the toolkit provides the support instead of a dedicated change lead. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 13 | AI ACCELERATOR

# AI Change Copilot Prompts

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Project Teams, Change Leads, Bronze users | When drafting first versions of delivery assets | 5-15 minutes | First-draft assets for human review | AI Accelerator |

Uses AI to accelerate drafting, synthesis, and tailoring while keeping human judgment in control.

| Field | Prompt / Fill-in |
| --- | --- |
| Change summary prompt | Create a concise change summary for [audience]. Explain why it matters, what is changing, what action is required, and where people can get help. |
| Manager one-pager prompt | Create a one-page manager briefing for [initiative]. Include what is changing, why it matters, team actions, manager reinforcement, and FAQs. |
| Behavior shift prompt | Create a before-and-after behavior shift canvas for [initiative]. Identify current behaviors, desired behaviors, friction points, and manager actions. |
| Bronze pack prompt | Create a Bronze self-service change pack with summary, manager script, FAQ, checklist, and success measure. |
| Risk scan prompt | Review this plan and identify adoption risks, saturation risks, missing owners, unclear behaviors, and recommended mitigations. |

|  | USEFULNESS CHECK How to make this useful AI drafts. Humans decide. Always check accuracy, context, audience fit, and business sensitivity before publishing. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

SECTION

# Section 2 | Leadership Enablement

From leader message to manager-led adoption. This section equips leaders and people managers to make change understandable, consistent, and repeatable through operating rhythms, manager enablement, listening loops, recognition, and Our DNA culture activation.

|  | PRINCIPLE Leadership principle Change lands or fails at the manager level. Leaders create alignment, managers translate the change into daily work, and teams adopt through repeated reinforcement. |
| --- | --- |

| Rhythm | Purpose | How it shows up |
| --- | --- | --- |
| Always-On Change Rhythm | Keep change visible, sequenced, and reinforced | Weekly leader guidance; office hours; biweekly manager enablement; monthly adoption checkpoint |
| Our DNA Engagement Rhythm | Connect work to culture, belonging, customer impact, and responsible AI | DNA Thread; monthly leader messages; All Hands inserts; recognition prompts |
| Manager Reinforcement Rhythm | Turn messages into team behavior | Manager Action Card; What To Do Next; Signals Pack; Top Heard / Top Changed |

## Always-On Operating Rhythm

| Cadence | Leader / manager action | Primary output |
| --- | --- | --- |
| Weekly | Leader guidance + Office Hours / AMA + publish top heard / changed | Current guidance, open questions, visible follow-through |
| Biweekly | Manager enablement pack + Signals Pack | Reinforce / Stop / Escalate actions for managers |
| Monthly | Adoption + org health checkpoint | Scorecard review, decisions, actions, saturation view |
| Always | Single intake, visible sequencing, readiness gates before scale | A live system that protects teams from overload and makes adoption visible |

## Our DNA Engagement Rhythm

|  | CULTURE ACTIVATION Positioning statement Our DNA becomes a practical, portable operating rhythm - helping every employee understand how to belong, contribute, use AI responsibly, and connect their work to eBay culture and strategy. |
| --- | --- |

| DNA Thread question | Prompt |
| --- | --- |
| 1. What are we focused on? | [Priority, initiative, behavior, or moment] |
| 2. Why does it matter? | [Business, teammate, customer, or operational reason] |
| 3. How does this connect to strategy and customers? | [Customer impact / eBay strategy connection] |
| 4. Which Our DNA behavior does this demonstrate? | [Be for Everyone / Deliver with Impact / Innovate Boldly / Act with Integrity / Empower Our Community] |
| 5. What real story makes this tangible? | [Employee or customer experience] |
| 6. What should employees know, do, question, or carry forward? | [Action or reflection] |

## Leadership Enablement Templates

| Leader Cascade Brief Align leaders before managers are expected to drive adoption. | Weekly Leader Guidance Create repeatable weekly clarity for leaders and managers. |
| --- | --- |
| Office Hours and AMA Template Create a two-way channel for questions and clarification. | Top Heard / Top Changed Update Close feedback loops and show visible follow-through. |
| Manager Action Card Give managers say/do/watch/escalate/recognize guidance. | Manager What To Do Next Guide Create a simple launch reinforcement rhythm. |
| Manager Enablement and Signals Pack Give managers one trusted source of truth with Reinforce/Stop/Escalate. | Monthly Adoption and Org Health Checkpoint Turn adoption data and org signals into leadership decisions. |
| DNA Thread Builder Connect priority, customer impact, culture, and action. | Monthly DNA Leader Message Make Our DNA visible in normal leadership communication. |
| All Hands DNA Insert Add one slide or segment connecting key work to DNA and customer impact. | Manager Cascade Guide 3/2/1 Help managers cascade culture and change with minimal prep. |
| Recognition Prompts Recognize how work gets done, not only what was delivered. | VoE / Listening Loop Template Use You Said / We Did to build trust and close loops. |
| AI Responsibility Prompt Normalize AI ethics, human judgment, and override protocols. |  |

TEMPLATE 14 | LEADERSHIP RHYTHM

# Leader Cascade Brief

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Sponsors, Change Leads | Before manager activation or major change moments | 20 minutes | Aligned narrative and leader decision ask | Leadership Rhythm |

Gives leaders a concise narrative, decision points, and reinforcement messages before managers are expected to drive adoption.

| Field | Prompt / Fill-in |
| --- | --- |
| What is changing? | [One clear sentence] |
| Why now? | [Business reason] |
| Why it matters to GCX | [Customer, teammate, operational, or strategic impact] |
| What success looks like | [Outcome and observable behavior] |
| What leaders need to reinforce | [Priority message, expected behavior, timing, decision] |
| What leaders should avoid saying | [Ambiguity / overpromising / just another update] |
| Decision needed | [Approve timing / tier / sequencing / resource] |
| DNA add-on | [Which Our DNA behavior does this demonstrate? What story makes this real?] |

|  | USEFULNESS CHECK How to make this useful Leaders do not need long decks. They need narrative, trade-offs, decisions, and reinforcement messages. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 15 | LEADERSHIP RHYTHM

# Weekly Leader Guidance

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Change Leads | Weekly, as part of the Always-On Operating Rhythm | 15 minutes | A short weekly guidance note leaders and managers can use | Leadership Rhythm |

Gives leaders a repeatable weekly message that connects priority, progress, and action.

| Field | Prompt / Fill-in |
| --- | --- |
| This week we are focused on | [Priority] |
| Why it matters | [Business, customer, teammate, operational reason] |
| What has changed since last week | [Decision, update, shift] |
| What leaders should reinforce | [Specific message or behavior] |
| What managers need to do | [Specific action] |
| What we are hearing | [Top signal] |
| What we are doing about it | [Action / owner / timing] |

|  | USEFULNESS CHECK How to make this useful Clear. Human. Action-oriented. No long context blocks. No vague optimism. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 16 | LEADERSHIP RHYTHM

# Office Hours and AMA Template

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Managers, Change Leads | Weekly or during high-impact change periods | 30-45 minutes | Top questions, open decisions, actions, and toolkit updates | Leadership Rhythm |

Creates a two-way channel for questions, friction, and fast clarification.

| Field | Prompt / Fill-in |
| --- | --- |
| Purpose | [What this session is for] |
| Audience | [Who should attend] |
| Topics in scope | [List] |
| Topics out of scope | [List] |
| Pre-read / source of truth | [Link] |
| Agenda | 5 min update / 15 min top questions / 20 min open friction / 10 min actions |
| After-session output | Top heard / top changed / open decisions / actions / owner / updates to manager pack or toolkit |

|  | USEFULNESS CHECK How to make this useful The value is not the meeting. The value is the visible update afterward. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 17 | LEADERSHIP RHYTHM

# Top Heard / Top Changed Update

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Managers, Change Leads | Weekly or after major listening moments | 10 minutes | A short trust-building update | Leadership Rhythm |

Closes feedback loops and builds trust through visible follow-through.

| Field | Prompt / Fill-in |
| --- | --- |
| Top heard | [What employees or managers are asking, feeling, or struggling with] |
| Top changed | [What has been clarified, fixed, sequenced, or escalated] |
| What is still open | [Unresolved items] |
| What happens next | [Action, owner, timing] |
| Where to follow updates | [Toolkit, channel, manager pack, office hours] |

|  | USEFULNESS CHECK How to make this useful Do not pretend every concern is resolved. Build trust by showing what changed because people spoke up. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 18 | LEADERSHIP RHYTHM

# Manager Action Card

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| People Managers, Change Leads, Project Teams | Two weeks before launch through the first month after launch | 15 minutes | Say / do / watch / escalate / recognize guidance | Leadership Rhythm |

Gives managers clear, practical guidance to lead adoption without overwhelming them.

| Field | Prompt / Fill-in |
| --- | --- |
| What is changing | [Plain-language description] |
| Why it matters | [Customer, teammate, operations, strategy] |
| Say this | [Short talking point managers can use] |
| Do this | [Specific manager action this week] |
| Watch for this | [Friction, confusion, old behavior, workarounds] |
| Escalate this | [Blocker, repeated question, risk, saturation issue] |
| Recognize this | [Behavior or early adoption to acknowledge] |
| Top FAQs | [3-5 suggested responses] |

|  | USEFULNESS CHECK How to make this useful Managers are not a comms channel. They are the adoption engine. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 19 | LEADERSHIP RHYTHM

# Manager What To Do Next Guide

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| People Managers | Two weeks before launch through four weeks after launch | 10 minutes weekly | Manager action rhythm | Leadership Rhythm |

Creates a simple weekly rhythm for reinforcing change before, during, and after launch.

| Field | Prompt / Fill-in |
| --- | --- |
| Two weeks before launch | Understand the change / review manager card / identify likely questions / raise concerns early |
| Launch week | Brief the team / explain what changes and why / show what to do differently / direct to support |
| Two weeks after launch | Check whether behavior is happening / reinforce in team meetings and 1:1s / share feedback / escalate blockers |
| Four weeks after launch | Confirm adoption signals / share lessons / reduce launch support dependency / sustain through normal rhythm |
| Ongoing | Recognize behavior, surface friction, and keep connecting work to customer impact and Our DNA |

|  | USEFULNESS CHECK How to make this useful Managers do not need theory. They need the next action, the message to use, and where to escalate friction. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 20 | LEADERSHIP RHYTHM

# Manager Enablement and Signals Pack

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| People Managers, Change Leads | Biweekly, or more frequently during major change | 20 minutes | Manager pack and action signals | Leadership Rhythm |

Gives managers one trusted source of truth and a simple Reinforce / Stop / Escalate action model.

| Field | Prompt / Fill-in |
| --- | --- |
| What is new | [Updates since last pack] |
| Reinforce | [Messages or behaviors to continue] |
| Stop | [Confusing guidance, workarounds, or old behaviors to stop] |
| Escalate | [Blockers, resistance, saturation issues, decision needs] |
| Team huddle script | [Short script] |
| Top 5 FAQs | [Questions and suggested answers] |
| Resources | [Links] |
| Feedback route | [Where managers send questions or friction] |

|  | USEFULNESS CHECK How to make this useful This should become a signature asset. It gives managers clarity and creates a feedback loop for leaders. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 21 | LEADERSHIP RHYTHM

# Monthly Adoption and Org Health Checkpoint

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Change Leads, Portfolio Owners | Monthly | 45-60 minutes | Decision log, action plan, updated saturation view, updated manager guidance | Leadership Rhythm |

Turns adoption data and organization signals into leadership decisions.

| Field | Prompt / Fill-in |
| --- | --- |
| Inputs | Change calendar / saturation view / adoption scorecard / manager confidence / resistance log / top heard-top changed / operational metrics |
| What is landing? | [Evidence] |
| What is not landing? | [Evidence] |
| Which audiences are saturated? | [Audience / risk / decision] |
| Where are managers struggling? | [Signal / action] |
| What needs a leader decision? | [Decision / owner / date] |
| Actions before next checkpoint | [Action plan] |

|  | USEFULNESS CHECK How to make this useful Do not use the checkpoint as status reporting. Use it to make decisions and remove adoption blockers. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 22 | LEADERSHIP RHYTHM

# DNA Thread Builder

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Managers, Comms, Change Leads | Any recurring communication, All Hands, team meeting, recognition, or leader update | 10 minutes | Culture-connected message or discussion prompt | Leadership Rhythm |

Connects priority, customer impact, culture, responsible AI, and action in one repeatable leadership communication pattern.

| Field | Prompt / Fill-in |
| --- | --- |
| What are we focused on? | [Priority, change, goal, or behavior] |
| Why does it matter? | [Customer / teammate / business connection] |
| How does this connect to eBay strategy and customers? | [Specific link] |
| Which Our DNA behavior does this demonstrate? | [Behavior and why] |
| What real experience brings this to life? | [Employee or customer story] |
| What should employees know, do, question, or carry forward? | [Action / discussion / reflection] |

|  | USEFULNESS CHECK How to make this useful Use DNA to explain how work gets done, not as a slogan attached after the fact. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 23 | LEADERSHIP RHYTHM

# Monthly DNA Leader Message

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| VPs, Directors, Leaders | Monthly | 15 minutes | Short leader message with priority, DNA connection, story, and next action | Leadership Rhythm |

Makes Our DNA visible in normal leadership communication.

| Field | Prompt / Fill-in |
| --- | --- |
| Priority | This month we are focused on [priority]. |
| Why it matters | This matters because [customer / teammate / business connection]. |
| DNA connection | This demonstrates [Our DNA behavior] because [reason]. |
| Story | A real example of this is [customer / employee story]. |
| What is next | The action I want you to take is [specific behavior]. |
| Question to carry forward | [Reflection or discussion question] |

|  | USEFULNESS CHECK How to make this useful Make it personal. Tie the DNA behavior to actual work. Avoid values as slogans without evidence. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 24 | LEADERSHIP RHYTHM

# All Hands DNA Insert

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Comms, Change Leads | VP All Hands, Director+ meetings, major town halls | 15 minutes | One-slide story spine for culture and strategy connection | Leadership Rhythm |

Adds a single slide or short segment that connects key work to Our DNA, customer impact, AI readiness, and recognition.

| Field | Prompt / Fill-in |
| --- | --- |
| Priority or change | [What are we anchoring?] |
| Customer / teammate impact | [Who benefits and how?] |
| Our DNA behavior | [Which behavior is demonstrated?] |
| Story-worthy moment | [Employee or customer example] |
| Responsible AI connection | [Where AI helps and where human judgment remains, if relevant] |
| Recognition moment | [Who or what behavior should be recognized?] |
| Call to action | [What should teams do next?] |

|  | USEFULNESS CHECK How to make this useful Keep it to one slide or one short segment. The purpose is connection, not content overload. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 25 | LEADERSHIP RHYTHM

# Manager Cascade Guide 3/2/1

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| People Managers | Weekly team meetings or after leader updates | 10 minutes | Three talking points, two discussion questions, one action | Leadership Rhythm |

Helps managers cascade culture and change with minimal prep.

| Field | Prompt / Fill-in |
| --- | --- |
| 3 talking points | 1. [What is happening] / 2. [Why it matters] / 3. [How this connects to Our DNA or customer impact] |
| 2 discussion questions | 1. What does this mean for our team? / 2. What support or clarity do we need to act on this? |
| 1 action | [Specific behavior, next step, or reflection to carry forward] |
| Feedback route | [Where team questions or friction go] |

|  | USEFULNESS CHECK How to make this useful This should fit into an existing team meeting. No extra meeting required. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 26 | LEADERSHIP RHYTHM

# Recognition Prompts

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Managers | Weekly or monthly recognition moments | 5 minutes | Values-led recognition tied to impact | Leadership Rhythm |

Recognizes how work gets done, not only what was delivered.

| Field | Prompt / Fill-in |
| --- | --- |
| Behavior observed | [What did the person or team do?] |
| Our DNA connection | [Be for Everyone / Deliver with Impact / Innovate Boldly / Act with Integrity / Empower Our Community] |
| Customer or teammate impact | [What improved because of it?] |
| AI spotlight, if relevant | [How AI was used responsibly with human judgment] |
| Recognition message | [Short recognition statement] |
| Reinforcement ask | [What behavior should others repeat?] |

|  | USEFULNESS CHECK How to make this useful Recognize the repeatable behavior, not just the hero moment. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 27 | LEADERSHIP RHYTHM

# VoE / Listening Loop Template

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| Leaders, Managers, Change Leads | Quarterly or after major listening moments | 20 minutes | Visible follow-through update | Leadership Rhythm |

Uses You Said / We Did to build trust and close feedback loops.

| Field | Prompt / Fill-in |
| --- | --- |
| You said | [What employees or managers raised] |
| We did | [What changed, was clarified, fixed, sequenced, or escalated] |
| What we are still working on | [Open item and why] |
| What happens next | [Action / owner / timing] |
| What we need from you | [Input, behavior, question, or action] |

|  | USEFULNESS CHECK How to make this useful Trust grows when people can see the loop close. Avoid over-polished updates that hide unresolved issues. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement

TEMPLATE 28 | AI ACCELERATOR

# AI Responsibility Prompt

| Best for | Use when | Time | Output | Template type |
| --- | --- | --- | --- | --- |
| All leaders and managers | When AI is part of the change or team workflow | 10 minutes | Responsible AI talking points and team discussion prompts | AI Accelerator |

Normalizes AI ethics, human judgment, explainability, and override protocols in leader and manager communication.

| Field | Prompt / Fill-in |
| --- | --- |
| Where AI helps | [Task, workflow, insight, efficiency, teammate support] |
| Where human judgment remains | [Decision, empathy, escalation, exception handling, quality review] |
| What employees should know | [Transparency, limits, expectations] |
| When to override AI | [Triggers, escalation route, confidence threshold] |
| How to explain it | [Simple language managers can use] |
| Team discussion question | [What support do we need to use this responsibly?] |

|  | USEFULNESS CHECK How to make this useful AI should elevate work, not create ambiguity. Leaders must explain where judgment remains. |
| --- | --- |

Back to Start Here  |  Project Delivery  |  Leadership Enablement